## 📋 Cover
🛡️ Enterprise Risk Register Template
A ready-to-use, professionally structured Risk Register aligned with ISO 31000, ISO 27005, NIST CSF and COSO ERM frameworks. Designed for enterprise risk managers, CISOs, compliance officers and internal auditors.
📋 HOW TO USE: Navigate to the tabs below. Blue cells are editable — all risk scores, levels and summaries calculate automatically. Start with the 'Risk Register' tab.
ABOUT INTERVALLE TECHNOLOGIES
🏆 18+ years of expertise • 300+ enterprise clients across 15 countries — Trusted partner in Cybersecurity, GRC & Business Solutions.
🎓 Certified experts: ISO 27001 Lead Auditor, PCI-DSS QSA, GDPR DPO, CISM, CISSP, CISA — Official partners: IBM, Symantec, PECB, ISC², ISACA.
🛡️ GRC Services: ISO 27001/27005 Audit • GDPR • NIS2 • PCI-DSS • SOX • Risk Mapping • Managed SOC • Penetration Testing.
🚀 GET EXPERT GRC SUPPORT — OUR CONSULTANTS RESPOND WITHIN 24 HOURS
| 📧 Request a Free GRC Audit | Get a no-obligation assessment of your risk management maturity from our certified consultants. | contact@intervalle-technologies.com
| 📅 Schedule a Free 30-Min Meeting | Discuss your ISO 27001, NIS2, GDPR or PCI-DSS challenges with a dedicated GRC expert. | contact@intervalle-technologies.com
| 💼 Explore Our GRC Services | Risk mapping, compliance audits, managed SOC, pen testing and more for large enterprises. | intervalle-technologies.com
| 🔒 Free Cybersecurity Assessment | Identify your critical vulnerabilities with a complimentary initial security review. | contact@intervalle-technologies.com
Intervalle Technologies® — contact@intervalle-technologies.com — www.intervalle-technologies.com ¦ © 2025 All Rights Reserved.

## 📊 Risk Register
🛡️ ENTERPRISE RISK REGISTER
Aligned with ISO 31000 ¦ ISO 27005 ¦ NIST CSF ¦ COSO ERM — Intervalle Technologies®
📋 INSTRUCTIONS: Fill in blue cells. Risk Score = Likelihood × Impact auto-calculates. Thresholds: 🔴 Critical ≥15 ¦ 🟠 High ≥9 ¦ 🟡 Moderate ≥4 ¦ 🟢 Low <4 ¦ 1 = Very Low 5 = Very High
Risk ID | Category | Risk Description | Risk Owner | Business Unit | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Level | Inherent Risk Level | Existing Controls | Treatment Strategy | Residual Risk Level | Action Plan / Next Steps | Due Date | Status | Last Reviewed | Notes / Comments
RSK-001 | Strategic | Failure to adapt to digital disruption — loss of competitive positioning | CEO | Executive | 3 | 4 | 12 | 🟠 High | High | Digital transformation roadmap in place | Mitigate |  | Launch innovation taskforce; accelerate digital roadmap | 2025-12-31 | In Progress | 2024-11-01 | Review quarterly with board
RSK-002 | IT / Cybersecurity | Ransomware attack on critical infrastructure | CISO | IT Security | 3 | 5 | 15 | 🔴 Critical | Critical | EDR deployed, MFA enforced, backups isolated | Mitigate |  | Deploy 24/7 managed SOC; annual pen test | 2025-06-30 | In Progress | 2024-11-15 | SOC provider selection underway
RSK-003 | Regulatory / Compliance | GDPR non-compliance — inadequate data processing records | DPO | Legal & Compliance | 3 | 4 | 12 | 🟠 High | High | Data protection policy v2 in place | Mitigate |  | Full GDPR audit; update Article 30 register | 2025-03-31 | In Progress | 2024-10-20 | 2 processing activities undocumented
RSK-004 | Regulatory / Compliance | NIS2 Directive compliance gaps across critical systems | CISO | IT Security | 3 | 5 | 15 | 🔴 Critical | Critical | Initial NIS2 gap analysis completed | Mitigate |  | NIS2 remediation program — CISO led | 2025-09-30 | Identified | 2024-11-01 | Board briefed, budget approved
RSK-005 | Financial | Fraudulent transactions — inadequate segregation of duties | CFO | Finance | 2 | 5 | 10 | 🟠 High | High | Dual approval for transactions >$50K | Mitigate |  | Strengthen access controls in ERP; internal audit | 2025-04-30 | In Progress | 2024-10-15 | 2 shared admin accounts identified
RSK-006 | IT / Cybersecurity | Critical data breach via third-party vendor | CISO | IT Security | 2 | 5 | 10 | 🟠 High | High | Vendor security questionnaire in place | Mitigate |  | Implement vendor risk scoring platform | 2025-06-30 | Identified | 2024-11-01 | 12 tier-1 vendors not assessed
RSK-007 | Operational | Key person dependency — loss of critical talent | CHRO | HR | 3 | 3 | 9 | 🟠 High | High | Retention bonuses, succession planning drafted | Mitigate |  | Formalize succession plan for top 20 roles | 2025-05-31 | In Progress | 2024-10-01
RSK-008 | Third-Party / Vendor | Critical supplier failure disrupts operations | CPO | Procurement | 3 | 4 | 12 | 🟠 High | High | SLA contracts in place | Mitigate |  | Dual-source critical suppliers; BCP update | 2025-04-15 | Identified | 2024-11-01 | 3 single-source dependencies
RSK-009 | IT / Cybersecurity | Unpatched vulnerabilities in legacy systems | CISO | IT | 4 | 3 | 12 | 🟠 High | High | Patch management policy exists | Mitigate |  | Automated patch deployment tool rollout | 2025-03-31 | In Progress | 2024-10-20 | 40% of systems on manual patching
RSK-010 | Regulatory / Compliance | PCI-DSS v4 compliance deadline — gaps in cardholder data env. | CISO | IT Security | 2 | 5 | 10 | 🟠 High | High | PCI-DSS v3.2 compliant; v4 gap analysis pending | Mitigate |  | Engage QSA; remediate cardholder data gaps | 2025-06-30 | Identified | 2024-11-01
RSK-011 | Environmental / ESG | Climate-related supply chain disruptions | COO | Operations | 2 | 3 | 6 | 🟡 Moderate | Moderate | Basic BCP in place | Accept |  | ESG risk assessment; climate scenario planning | 2025-12-31 | Identified | 2024-09-01 | ESG report due Q2 2025
RSK-012 | Legal | Class action lawsuit — product liability | General Counsel | Legal | 1 | 5 | 5 | 🟡 Moderate | Moderate | Insurance coverage; legal team on retainer | Transfer |  | Review insurance coverage limits | 2025-03-31 | Identified | 2024-10-01 | Coverage renewal March 2025
RSK-013 | IT / Cybersecurity | Insider threat — unauthorized data exfiltration | CISO | IT Security | 2 | 4 | 8 | 🟡 Moderate | Moderate | DLP partially deployed; UEBA not in place | Mitigate |  | Full DLP rollout; UEBA implementation | 2025-07-31 | Identified | 2024-11-01
RSK-014 | HR / People | Workplace safety incidents — manufacturing sites | CHRO | Operations | 2 | 3 | 6 | 🟡 Moderate | Moderate | HSE training program; monthly site audits | Mitigate |  | Upgrade PPE standards; increase audit frequency | 2025-06-30 | In Progress | 2024-10-15
RSK-015 | Regulatory / Compliance | Tax compliance risk across multiple jurisdictions | CFO | Finance | 2 | 4 | 8 | 🟡 Moderate | Moderate | External tax advisor retained | Transfer |  | Annual tax risk review; transfer pricing update | 2025-09-30 | Identified | 2024-09-01
RSK-016 | [6 empty] | 0 | 🟢 Low | Low
RSK-017 | [6 empty] | 0 | 🟢 Low | Low
RSK-018 | [6 empty] | 0 | 🟢 Low | Low
RSK-019 | [6 empty] | 0 | 🟢 Low | Low
RSK-020 | [6 empty] | 0 | 🟢 Low | Low
RSK-021 | [6 empty] | 0 | 🟢 Low | Low
RSK-022 | [6 empty] | 0 | 🟢 Low | Low
RSK-023 | [6 empty] | 0 | 🟢 Low | Low
RSK-024 | [6 empty] | 0 | 🟢 Low | Low
RSK-025 | [6 empty] | 0 | 🟢 Low | Low
RSK-026 | [6 empty] | 0 | 🟢 Low | Low
RSK-027 | [6 empty] | 0 | 🟢 Low | Low
Intervalle Technologies® ¦ Cybersecurity & GRC Experts ¦ contact@intervalle-technologies.com ¦ www.intervalle-technologies.com
📧 Request a Free GRC Audit ¦ 📅 Schedule a 30-Min Expert Call → contact@intervalle-technologies.com ¦ 🌐 intervalle-technologies.com

## 📈 Dashboard
📈 RISK REGISTER — EXECUTIVE DASHBOARD
Intervalle Technologies® — Auto-calculated from the Risk Register tab. For use in CISO reports, Risk Committees & Board presentations.
| 🔴 Critical Risks |  |  |  | 🟠 High Risks |  |  |  | 🟡 Moderate Risks
| 2 |  |  |  | 8 |  |  |  | 5
| 🟢 Low Risks |  |  |  | 📋 Total Risks |  |  |  | 📊 Avg Risk Score
| 12 |  |  |  | 27 |  |  |  | 10
| RISK DISTRIBUTION BY CATEGORY |  |  |  |  | RISK STATUS BREAKDOWN
| Category | # Risks | Avg Score | Status |  | Status | Count | % of Total
| Strategic | 1 | 12 | ⚠️ Attention |  | Identified | 8 | 29.63%
| Operational | 1 | 9 | ⚠️ Attention |  | In Progress | 7 | 25.93%
| Financial | 1 | 10 | ⚠️ Attention |  | Treated | 0 | 0%
| IT / Cybersecurity | 4 | 11.25 | ⚠️ Attention |  | Accepted | 0 | 0%
| Regulatory / Compliance | 4 | 11.25 | ⚠️ Attention |  | Closed | 0 | 0%
| HR / People | 1 | 6 | ✅ Managed |  | On Hold | 0 | 0%
| Environmental / ESG | 1 | 6 | ✅ Managed
| Third-Party / Vendor | 1 | 12 | ⚠️ Attention
| Legal | 1 | 5 | ✅ Managed
Intervalle Technologies® ¦ contact@intervalle-technologies.com ¦ www.intervalle-technologies.com — Request your Free GRC Audit Today

## 📖 Scoring Guide
📖 RISK SCORING GUIDE & METHODOLOGY
Reference guide for consistent risk assessment — Aligned with ISO 31000 ¦ ISO 27005 ¦ NIST CSF
LIKELIHOOD SCALE
| Score | Level | Description | Example Trigger | Frequency
| 1 | Very Low | Highly unlikely to occur | No historical occurrence; theoretical only | < Once in 10 years
| 2 | Low | Unlikely but possible | Occurred in industry, not at organization | Once in 5–10 years
| 3 | Moderate | Reasonably possible | Has occurred once in the organization | Once in 2–5 years
| 4 | High | Likely to occur | Occurs periodically in the organization | Once per year
| 5 | Very High | Almost certain to occur | Frequent occurrence; ongoing exposure | Multiple times per year
IMPACT SCALE
| Score | Level | Financial Impact | Operational Impact | Reputational Impact
| 1 | Negligible | < $10,000 | Minimal disruption < 1 hour | No public awareness
| 2 | Minor | $10K – $100K | Partial disruption < 1 day | Limited internal impact
| 3 | Moderate | $100K – $1M | Significant disruption 1–3 days | Some media coverage
| 4 | Major | $1M – $10M | Critical disruption 3–7 days | Major media / regulatory scrutiny
| 5 | Catastrophic | > $10M | Full operational failure > 1 week | Severe reputational / regulatory damage
RISK LEVEL MATRIX (Score = Likelihood × Impact)
| Treatment Requirement |  | Score Range
| 🔴 Critical | ≥ 15 (e.g. 3×5, 4×4, 5×3) | Immediate executive action required. Risk committee escalation mandatory. Treatment plan within 30 days.
| 🟠 High | 9 – 14 (e.g. 3×3, 2×5) | Senior management attention required. Formal treatment plan within 60 days.
| 🟡 Moderate | 4 – 8 (e.g. 2×2, 2×4) | Management oversight needed. Treatment plan within 90 days.
| 🟢 Low | 1 – 3 (e.g. 1×1, 1×3) | Monitor and review periodically. Accept or include in standard risk reviews.
RISK TREATMENT STRATEGIES
| Strategy | Definition | When to Apply | Examples
| Mitigate | Reduce the likelihood and/or impact | Risk level High or Critical; cost of control < cost of risk | Deploy EDR, patch management, access controls, staff training
| Transfer | Shift the financial consequence to a third party | Residual risk remains; insurance or outsourcing feasible | Cyber insurance, SLA penalties, outsourced managed services
| Avoid | Eliminate the risk by stopping the activity | Risk is unacceptable; activity not essential to business | Discontinue a product line, exit a high-risk market
| Accept | Acknowledge the risk without further action | Risk level Low; cost of treatment > potential impact | Document and monitor; senior sign-off required
Intervalle Technologies® ¦ Cybersecurity & GRC Experts ¦ contact@intervalle-technologies.com
📧 Need help implementing this framework in your organization? Request a Free ISO 31000 Risk Assessment → contact@intervalle-technologies.com